## milestones
[5 empty] | rooms in ELEC unless otherwise noted | drone lokaal = 00.62 | # persons | ESCs | # persons | Inductive power | # persons | Control | # persons | Vision | # persons | Wireless video | # persons | Crypto | Total # persons
Day | Date | Begin | End | What and who | Where (ordered as in the previous columns) | gewenst
Monday | 2016-09-26 | 13:30 | 16:00 | Academic year opening
Monday | 2016-09-26 | 16:00 | 18:30 | Academic year opening
Tuesday | 2016-09-27 | 16:00 | 18:30
Monday | 2016-10-03 | 13:30 | 16:00 | Introduction, all groups |  | auditorium
Monday | 2016-10-03 | 16:00 | 18:30 | Brainstorm taakverdeling + planning |  | 4 leslokalen (geen auditoria!)
Tuesday | 2016-10-04 | 16:00 | 18:30
Understand & plan phase
Monday | 2016-10-10 | 13:30 | 16:00 | worksession1.1 |  | 3 computerklassen+drone lokaal
Monday | 2016-10-10 | 16:00 | 18:30 | worksession1.2 |  | 3 computerklassen+drone lokaal
Tuesday | 2016-10-11 | 16:00 | 18:30
Monday | 2016-10-17 | 13:30 | 16:00 | worksession2.1 |  | 3 computerklassen+drone lokaal
Monday | 2016-10-17 | 16:00 | 18:30 | worksession2.2 |  | 3 computerklassen+drone lokaal
Tuesday | 2016-10-18 | 16:00 | 18:30
Monday | 2016-10-24 | 13:30 | 16:00 | worksession3.1 |  | 3 computerklassen+drone lokaal
Monday | 2016-10-24 | 16:00 | 18:30 | worksession3.2 |  | 3 computerklassen+drone lokaal
Tuesday | 2016-10-25 | 16:00 | 18:30
T1: project gantt chart + person allocations | [15 empty] | VHDL blocks compiled
Modeling phase
Monday | 2016-10-31 | 13:30 | 16:00 | worksession4.1 |  | 3 computerklassen+drone lokaal
Monday | 2016-10-31 | 16:00 | 18:30 | worksession4.2 |  | 3 computerklassen+drone lokaal
Tuesday | 2016-11-01 | 16:00 | 18:30 | All Saints' Day
Monday | 2016-11-07 | 13:30 | 16:00 | worksession5.1 |  | 3 computerklassen+drone lokaal
Monday | 2016-11-07 | 16:00 | 18:30 | worksession5.2 |  | 3 computerklassen+drone lokaal
Tuesday | 2016-11-08 | 16:00 | 18:30
Monday | 2016-11-14 | 13:30 | 16:00 | worksession6.1 |  | 3 computerklassen+drone lokaal
Monday | 2016-11-14 | 16:00 | 18:30 | worksession6.2 |  | 3 computerklassen+drone lokaal
Tuesday | 2016-11-15 | 16:00 | 18:30
Monday | 2016-11-21 | 13:30 | 16:00 | worksession7.1 |  | 3 computerklassen+drone lokaal
Monday | 2016-11-21 | 16:00 | 18:30 | worksession7.2 |  | 3 computerklassen+drone lokaal
Tuesday | 2016-11-22 | 16:00 | 18:30
Monday | 2016-11-28 | 13:30 | 16:00 | poster + model demos E1-E5, worksession8.1 E6-E10 |  | 01.57 + 00.60 + 3 computerklassen+drone lokaal |  | Demo on breadboard |  | Demo on breadboard |  | Demo of attitude and navigation in simulation |  | Demo of red line detection |  | Demo on video streaming
Monday | 2016-11-28 | 16:00 | 18:30 | poster + model demos E5-E10, worksession8.1 E1-E5 |  | 01.57 + 00.60 + 3 computerklassen+drone lokaal
Tuesday | 2016-11-29 | 16:00 | 18:30
T2 | [7 empty] | Open loop breadboard design done |  | Design finished and first prototype |  |  |  | Red line detection finished |  | Video streaming demonstrated
Module phase
Monday | 2016-12-05 | 13:30 | 16:00 | worksession9.1 |  | 3 computerklassen+drone lokaal | 1 |  | 1 |  | 2 |  | 2 |  | 2 |  | 0
Monday | 2016-12-05 | 16:00 | 18:30 | worksession9.2 |  | 3 computerklassen+drone lokaal | 1 |  | 1 |  | 2 |  | 2 |  | 2 |  | 0
Tuesday | 2016-12-06 | 16:00 | 18:30
Monday | 2016-12-12 | 13:30 | 16:00 | worksession 10.1 + pcb reworking |  | 3 computerklassen+drone lokaal | 1 |  | 1 |  | 2 |  | 2 |  | 2 |  | 0
Monday | 2016-12-12 | 16:00 | 18:30 | worksession 10.2 + pcb reworking |  | 3 computerklassen+drone lokaal | 1 |  | 1 |  | 2 |  | 2 |  | 2 |  | 0
Tuesday | 2016-12-13 | 16:00 | 18:30 |  |  |  |  | PCB design finished
T3: Hovering drone, manual control, video transmitted, commercial ESCs | [7 empty] | PCB design finished |  | PCB design finished |  | attitude control on drone |  | red line detection & localization finished |  | Video streaming on drone |  | /
Beginning of 2nd semester
Monday | 2017-02-13 | 13:30 | 16:00 | worksession11.1 |  | 3 computerklassen+drone lokaal
Tuesday | 2017-02-14 | 13:30 | 16:00 | worksession11.2 |  | 3 computerklassen+drone lokaal
Tuesday | 2017-02-14 | 16:00 | 18:30 | worksession11.3 |  | 3 computerklassen+drone lokaal
Monday | 2017-02-20 | 13:30 | 16:00 | worksession12.1 |  | 3 computerklassen+drone lokaal
Tuesday | 2017-02-21 | 13:30 | 16:00 | worksession12.2 |  | 3 computerklassen+drone lokaal
Tuesday | 2017-02-21 | 16:00 | 18:30 | worksession12.3 |  | 3 computerklassen+drone lokaal
Monday | 2017-02-27 | 13:30 | 16:00 | worksession13.1 |  | 3 computerklassen+drone lokaal
Tuesday | 2017-02-28 | 13:30 | 16:00 | worksession13.2 |  | 3 computerklassen+drone lokaal
Tuesday | 2017-02-28 | 16:00 | 18:30 | worksession13.3 |  | 3 computerklassen+drone lokaal
Monday | 2017-03-06 | 13:30 | 16:00 | worksession14.1 |  | 3 computerklassen+drone lokaal
Tuesday | 2017-03-07 | 13:30 | 16:00 | worksession14.2 |  | 3 computerklassen+drone lokaal
Tuesday | 2017-03-07 | 16:00 | 18:30 | worksession14.3 |  | 3 computerklassen+drone lokaal
Monday | 2017-03-13 | 13:30 | 16:00 | poster + module demos E1-E5, worksession 15.1 E6-E10 |  | 02.58, 00.60, 3 computerklassen+drone lokaal |  | demo with motor on table stand |  | demo with PCB and load provided |  | demo of navigation control (simple maneuvres) |  | demo of QR detection
Tuesday | 2017-03-14 | 13:30 | 16:00 | poster + module demos E6-E10, worksession 15.1 E1-E5 |  | 02.58, 00.60, 3 computerklassen+drone lokaal
T4 : Simple navigation maneuvres | [7 empty] | ESCs ready |  |  |  | navigation control on drone |  | QR detection finished |  |  |  | Python tests for cipher
Integration phase
Tuesday | 2017-03-14 | 16:00 | 18:30 | worksession15.2 |  | 3 computerklassen+drone lokaal
Monday | 2017-03-20 | 13:30 | 16:00 | worksession16.1 |  | 3 computerklassen+drone lokaal
Tuesday | 2017-03-21 | 13:30 | 16:00 | worksession16.2 |  | 3 computerklassen+drone lokaal
Tuesday | 2017-03-21 | 16:00 | 18:30 | worksession16.3 |  | 3 computerklassen+drone lokaal
Monday | 2017-03-27 | 13:30 | 16:00 | worksession17.1 |  | 3 computerklassen+drone lokaal
Tuesday | 2017-03-28 | 13:30 | 16:00 | worksession17.2 |  | 3 computerklassen+drone lokaal
Tuesday | 2017-03-28 | 16:00 | 18:30 | worksession17.3 |  | 3 computerklassen+drone lokaal
T5 | [7 empty] | Flying with own ESCs |  | Wireless power transfer from drone to load |  | Follow at least two checkpoints | [5 empty] | decryption on PC finished
Easter Holidays
Monday | 2017-04-17 | 13:30 | 16:00 | Easter Monday | [14 empty] | 0
Tuesday | 2017-04-18 | 13:30 | 16:00 | worksession18.1 |  | 3 computerklassen+drone lokaal
Tuesday | 2017-04-18 | 16:00 | 18:30 | worksession18.2 |  | 3 computerklassen+drone lokaal
Monday | 2017-04-24 | 13:30 | 16:00 | worksession19.1 |  | 3 computerklassen+drone lokaal
Tuesday | 2017-04-25 | 13:30 | 16:00 | worksession19.2 |  | 3 computerklassen+drone lokaal
Tuesday | 2017-04-25 | 16:00 | 18:30 | worksession19.3 |  | 3 computerklassen+drone lokaal
Monday | 2017-05-01 | 13:30 | 16:00 | International Workers' Day
Tuesday | 2017-05-02 | 13:30 | 16:00 | worksession20.1 |  | 3 computerklassen+drone lokaal
Tuesday | 2017-05-02 | 16:00 | 18:30 | worksession20.2 |  | 3 computerklassen+drone lokaal
Monday | 2017-05-08 | 13:30 | 16:00 | worksession21.1 |  | 3 computerklassen+drone lokaal
Tuesday | 2017-05-09 | 13:30 | 16:00 | worksession21.2 |  | 3 computerklassen+drone lokaal
Tuesday | 2017-05-09 | 16:00 | 18:30 | worksession21.3 |  | 3 computerklassen+drone lokaal
Monday | 2017-05-15 | 13:30 | 16:00 | worksession22.1 |  | 3 computerklassen+drone lokaal
Tuesday | 2017-05-16 | 13:30 | 17:30 | final presentations all groups |  | drone lokaal en 1 computerklas (02.53 of 02.54)
T6: Full mission | [7 empty] | fully integrated |  | fully integrated |  | fully integrated |  | fully integrated |  | fully integrated |  | fully integrated
Tuesday | 2017-05-16 | 17:30 | ? | closing reception all groups |  | receptielokaal
Monday | 2017-05-22 | 13:30 | 16:00 | closing session all groups |  | auditorium
Tuesday | 2017-05-23 | 13:30 | 16:00
Tuesday | 2017-05-23 | 16:00 | 18:30

## milestones_short
|  |  | Electronic Speed Control | Wireless Video Link | Attitude and Navigation Control | Image Processing | Cryptography | Wireless Power Transfer
Project Phase | Deadline | Global milestones
Understand & Plan phase | T1 | project gantt chart + person allocations |  | VHDL blocks compiled
Modeling phase | T2 | First set of demos ready | Open loop breadboard design done | Video streaming demonstrated |  | Red line detection finished |  | Design finished and first prototype
Module phase | T3 | Hovering drone, manual control, video transmitted, commercial ESCs | PCB design finished | Video streaming on drone | attitude control on drone | red line detection & localization finished |  | PCB design finished
| T4 | Simple navigation maneuvres | ESCs ready |  | navigation control on drone | QR detection finished | Python tests for cipher
Integration phase | T5 |  | Flying with own ESCs |  | follow at least two checkpoints |  | Decryption on PC finished | Wireless power transfer from drone to load
| T6 | Full mission