## milestones_short
|  |  | Electronic Speed Control | Wireless Video Link | Attitude and Navigation Control | Image Processing | Cryptography | Wireless Power Transfer
Project Phase | Deadline | Global milestones
Understand & Plan phase | T1 | project gantt chart + person allocations |  | VHDL blocks compiled
Modeling phase | T2 | First set of demos ready | Open loop breadboard design done | Video streaming demonstrated |  | Red line detection finished |  | Design finished and first prototype
Module phase | T3 | Hovering drone, manual control, video transmitted, commercial ESCs | PCB design finished | Video streaming on drone | attitude control on drone | red line detection & localization finished |  | PCB design finished
| T4 | Simple navigation maneuvres | ESCs ready |  | navigation control on drone | QR detection finished | Python tests for cipher
Integration phase | T5 |  | Flying with own ESCs |  | follow at least two checkpoints |  | Decryption on PC finished | Wireless power transfer from drone to load
| T6 | Full mission